## 工作表1
ID | Story | Estimation(Hours) | Priority(1-5) | sprint when Finished
1 | Creat application framework | 1 | 1 | 1
2 | Application GUI design | 5 | 1 | 1
3 | Figma Prototpye design | 1 | 1 | 1
4 | Allow user to choose between Covid Info or Vaccine Info | 0.5 | 2 | 1
5 | Allow user to choose self assesment, general info, and case map in Covid Info | 0.5 | 2 | 1
6 | Allow user to choose general info, eligibility and appointment scheduler/reminder in Vaccine Info | 0.5 | 2 | 1
7 | Collect Covid-19 information and Vaccince information | 6 | 1 | 1
8 | Design questionare for COVID-19 assessment and vaccine assessment | 3 | 3 | 1
9 | Allow user to create user name, password | 2 | 3 | 1
10 | Allow user to login | 1 | 5 | 1
11 | Allow user to creat a new password when they forget password | 1 | 5 | 1
12 | provide user the password advice | 1 | 5 | 1